## Sheet1
The 2013 Great Alberta Flood: Actions to Mitigate, Manage and Control Future Floods - Progress Report - March 2014
White Paper Recommendation | Specific Recommended Action | Activity to Date | Planned Next Steps | Gap? | Your Ideas
1. Anticipate and plan for more extreme weather events, including both flood and drought. | Analyze the confluence of events that resulted in the 2013 flood | Alberta Environment and Sustainable Resource Development's River Forecast Centre (RFC) currently looking at origins of the storm, and intial conditions that resulted in the flood | Consultant lead event assessments are currently underway, report to be released sometime in April | No
|  | The Bow River Operational Model (BROM) has been engaged to understand the specific impacts and streamflow rates generated by the 2013 flood (Alberta WaterSMART) | Releasing the modeling results at the Bow River Forum on March 12th and incorporating those results into Engineering Design Assessments | No
|  | Environment Canada currently looking at origins of the storm that resulted in the flood |  | No
| Overlay potential development scenarios on the weather scenarios | AI-EES/Alberta WaterSMART BROM Modeling project |  | No
| Determine the magnitude of potential economic loss from another flood event | Insurance Bureau of Canada has assessed that the estimate of insured property damage caused by the flood exceeds $1.7 billion (as of September 2014). This is a good starting point for an assessment of cost of future floods. |  | Yes
| Take a holistic approach when analyzing storm, flood and drought data | Government of Alberta has committed to taking a watershed wide approach and published the "Resilience and Mitigation Framework for Alberta Floods" framework in December 2013 |  | No
2. Improve our operational capacity to deal with potential extreme weather scenarios through better modeling and data management. | Ensure that data is available and easily accessible so that it can be used in modeling and planning by researchers, municipalities, provincial officials and private property owners | Key recommendation at AI-EES Flood Forecasting workshop was that the Government of Alberta needs to make data easily accessible and more readily available | Recommendation is being included in a workshop summary report, to be released by the end of April 2014. Funding is in place for a river basin redesign to allow for greater access to data | No
| Investigate back-up systems for Water Survey of Canada gauging systems to maintain data continuity during large events | Environment Canada is looking at how to make gauging stations more robust |  | No
| Improve predictive capacity through increased modeling and data management | AI-EES/Alberta WaterSMART Flood Indicators Project: - Jurisdictional research on flood forecasting best practices within Canada and around the world -Workshop complete in mid-Febrary that involved presentations from and discussions with local and international experts | AIEES/Alberta WaterSMART Flood Indicators Project: -Issue two summary reports outlining key findings from the jurisdictional research and the key discussion points and recommendations from the workshop -Post both reports on the WaterPortal for public review and comment | No
|  | Work by the RFC: - Investigation of how changes in duration and intensity of rainfall affect the timing of flood events (completion expected June 30, 2014) - RFC defining the hydrologic and hydraulic characteristics of the 2013 flood to assess, with the affected community, the need for a full flood mapping review (completion expected April 2014) - Investigation of best practices in river forecasting worldwide and potential performance measures that can be incorporated into the RFC annual review process to aid in model and program improvement (completion expected May 16, 2014) - Evaluate general uncertainty of current weather models used in various jurisdictions for both accuracy of location, lead time accuracy and amount accuracy to develop a plan to manage this uncertainty before and during flood events to evaluate the effect of variations in weather forecasts and the impact on river forecasting (completion expected May 16, 2014) |  | No
|  | Developing communication tools has been identified as a recommended action in the AI-EES Flood Forecasting workshop. Publicly available and user friendly tools are needed to help engage and educate the public with respect to high flood risk areas | Developing specific tools and communication methods | No
|  | Increasing and maintaining GoA flood risk mapping to be used in conjunction with visulaization tools such as BROM |  | Yes
|  | Recommendation to use integrated models that combine meteorological and hydrological data from AI-EES Flood Forecasting workshop | RFC working with Environment Canada to automate the linkage between their weather model gridded output and RFC runoff models | No
|  | Government of Alberta/ academics investigate and use best available technologies. Options include; American GRACE satellite and the new Canadian RADARSAT constellation satellite that can be used for better groundwater mapping. |  | Yes
|  | City of Calgary has assembled an Expert Management Panel to river modeling and forecasting and flood mapping as well as weather prediction, river flow monitoring, interagency cooperation and data sharing | Final report to be released in summer 2014 | No
|  | AI-EES/ Alberta WaterSMART BROM Modelling Project: increasing basin-specific modelling. Discussion on using BROM as an operational support tool for water managers and reservoir operators in training exercises. |  | No
| Recognize that flood and drought planning are interconnected, and that both should receive an equal amount of attention | Government of Alberta has committed to taking a watershed wide approach and published the "Resilience and Mitigation Framework for Alberta Floods" framework in December 2013. This framework recognizes that the government will "look at a suite of mitigation options that minimize future risk of flooding and that create a more resilient environment in the event of a flood or drought occurring." |  | No
| Develop a better understanding of the relationship between flooding and groundwater | Alberta WaterSMART proposal Groundwater and Flooding: Understanding the Risks was submitted to the Flood Recovery Task Force, Calgary Foundation and the Sunnyside/Hillhurst community association | Continue to encourage the Alberta Government, City of Calgary, etc., to address risks associated with groundwater flooding. In addition to understanding the risks assoicated with groundwater flooding, the groundwater environment and the role it plays prior to, during and after flooding events needs to be better understood. This requires a holistic understanding of groundwater resources and how it interacts with climate variability, precipitation, land use practices, vegetation cover, soil moisture, snow pack, spring run-off, etc. Understanding this dynamic is not only important from a flooding perspective but is also extremely important for managing and planning for drought | Yes
|  | City of Calgary Water Services and Sunnyside Flood Task Force are currently upgrading storm water infrastructure in community of Sunnyside |  | No
| Re-evaluate the potential for slumps and mudslides during flood events |  |  | Yes
| Build upon work that has already been done | Alberta WaterSMART's Historical Study of Diversion and Detention Sites on the Elbow River |  | No
|  | Alberta Water Portal's Historical Review of Flood Mitigation options on the Red Deer and Athabasca watersheds |  | No
| Engage public health professionals in assessing mitigation measures | Risk management measures for protecting drinking water and assessment of the effectiveness of boil water advisories should be pursued by municipalities and the GoA |  | Yes
3. Investigate the cost/benefit balance of investing in physical infrastructure such as on and off-stream storage, diversions, and natural infrastructure such as wetlands. | Conduct cost-benefit and risk analyses to assess the best use of capital funds to support infrastructure spending decisions | Cost benefit analysis was required for Flood Recovery Erosion Control (FREC) program. No overarching cost-benefit and risk analyses to assess the best use of capital funds to support infrastructure spending decisions have been undertaken. |  | Yes
| Consider all available infrastructure options | Dikes currently being built in High River | Discussions occuring about upgrades at Travers and Glenmore, depending on results of Highwood diversions | No
|  | Channel and reservoir debris clearing in several municipalities to improve conveyance (Calgary, High River, Canmore) | Power back-up systems to keep power on, more room to isolate systems | No
|  | Erosion protection on banks to 100-year level in the planning stages. Government of Alberta Erosion Control Program has approved $75 million for muncipal erosion control projects. |  | No
|  | Government of Alberta conducting feasibility studies for water diversion channel in High River and Dry Dam near Bragg Creek. |  | No
|  | City of Calgary has assembled an Expert Management Panel to examine water storage and diversion options; local flood protection from surface and groundwater; and drainage system standards |  | No
|  | City of Calgary conducting feasibility study for underground flood tunnel |  | No
| Use the best available risk assessment tools | Use of assessment tools such as those developed by the PIEVC. |  | Yes
| Implement the recommendations of the Bow River Project | AI-EES/ Alberta WaterSMART BROM Modeling Project |  | No
| Utilize on-stream storage for flood control | TransAlta and municipalities are updating flood action plans and operating practices based on 2013 outcomes |  | No
|  | AI-EES/ Alberta WaterSMART BROM Modeling Project: Developing a flow/flood damage relationship for Banff, Canmore, Morley, Cochrane, Calgary, Carseland, Siksika, Medicine Hat and other siginifcant communities and infrastructure |  | No
|  | Continue with operations that were successful in 2013 such as Glenmore Reservoir for flood mitigation. Prepare a basin-wide decision tree for operations (look at basin as one) (BROM) |  | No
| Utilize off-stream storage more effectively for flood mitigation | AI-EES/ Alberta WaterSMART BROM Modeling Project: Engaging the Western, Bow River and Eastern Irrigation Districts in a discussion as to how they can further utilize their infrastructure to help mitigate flood risk, while ensuring a robust response to drought conditions |  | No
| Improve management of headwater areas so that natural wetlands and riparian zones continue to act as a buffer for heavy rainfall | AI-EES/ Alberta WaterSMART BROM Modeling Project |  | Yes
| Incorporate natural infrastructure such as wetlands, riparian areas, natural storage conditions and land cover into flood and drought mitigation planning | GoA released the draft SSRP with some measures to protect headwaters. The final version may have more measures for headwater protection. |  | No
|  | Ducks Unlimited Report "Wetland Conservation and Restoration as Flood Mitigation Tools in the Bow River Basin" released January 2014 alongside flooding fact-sheet for the Bow River Basin |  | No
| Investigate and identify sparsely habited or uninhabited areas that could be potentially flooded with minimal economic and environmental impact | Rewilding our River blog series on the Alberta WaterPortal and work done by Kevin Van Tighem to shed light on this issue/ approach |  | No
|  | AI-EES/Alberta WaterSMART BROM Modeling project |  | No
4. Consider flood risks in municipal planning and strengthen building codes for new developments in flood plains. | Conduct cost-beneft and risk analyses to assess the best use of capital funds to support municipal planning and land use decisions | Municipalities should create a basis for evaluating the benefits of enhanced building codes and zoning plans against the costs of their implementation |  | Yes
| New municipal development in potentially flood-prone areas must be reconsidered | GoA non-voluntary buy-outs in High River and Wallaceville |  | No
|  | City of Calgary rebuilding pedestrian bridges to be stronger and more resiliant in the event of a flood. Will be built by end of 2014 |  | No
| Land use planning should be connected to watershed planning | Integrated land management and long-term implementation being pursued in Calgary and High River |  | No
|  | GoA to updated the SSRP to refer to flooding | Inclusion of flood risk aversion in the next draft of the SSRP | No
| Refine our zoning and building codes | New provincial government legislation restricts building in floodways. No review of world class zoning and building code practices for office towers, condominiums, residential homes and businesses has been undertaken |  | Yes
| Recognize the importance of urban stormwater run-off management | Town of Chestermere is updating their Master Area Structure Plan to address stormwater runoff |  | No
| Encourage APEGA to revise and update their practice standards to include assessments of risks due to natural disasters | APEGA encourages engineering firms to apply for flood mitigation projects, however, internal practices have not yet changed |  | No
| Make a variety of tools widely available to all Albertans to keep them informed during a flood event | The River Forecast Centre in Alberta is working to develop an "App" that will provide easy access to river basin flow, precipitation and snow data as well as any advisories currently in effect |  | No
|  | At the AIEES Flood Forecasting workshop, experts discussed the need for improved warning systems. A summary report of their recommendations will be released in April 2014 |  | No
5. Evaluate options for overland flood insurance. |  | Federal government committed to exploring this in the 2014 budget |  | No
|  | Co-operators Group Report: "Assessing the Viability of Overland Flood Insurance: The Canadian Residential Property Market" released in September 2013 |  | No
|  | Report released by the Institute for Catastrophic Loss Reduction put out a report - "Best Practices for reducing the risk of future damage to homes from riverine and urban flooding" |  | No
|  | Insurance industry stated there would be no overland flood insurance until flood hazard maps are updated | Alberta government pledged to update flood hazard maps | No
6. Manage our water resources collaboratively, following the examples of the Bow River Consortium and the Cooperative Stormwater Management Initiative, and ensure Watershed Planning and Advisory Councils (WPACs) across the province have proper authority and funding. | Support WPACs to work with their memberships to assess flood risk, consequences, and mitigation strategies and to provide advice to GoA | AI-EES/ Alberta WaterSMART BROM Modeling project helping BRBC |  | No
|  | GoA in regular consultation with BRBC, especially in December with meeting on flood mitigation ideas |  | No
| Consider creating a Provincial Water Authority |  |  | Yes
| Support and provide increased capacity to smaller municipalities to respond to natural disasters | Communities such as High River and Canmore have received provincial government assistance |  | No
7. Other | Response to 2013 Flood | GoA to ensure expedient delivery of Disaster Relief Program funding to impacted Albertans | Looking at moving into a case-worker program (i.e. High River has a lobby group that is pursuing this solution) | No
|  | Mental health: funding has been provided to mental health groups and a study of the impacts of the flooding on mental health and wellbeing is being done at the University of Calgary |  | No
| Emergency Management | Procure supplies (rocks, sandbags, water tubing) so there is enough on hand every spring |  | No
|  | Alberta Parks and TransAlta should have staff at remote sites with back-up communications and supplies to get through flood season |  | No
|  | Set up contract agreements ahead of time so contractors can mobilize quickly to help (as done in Calgary). For example, RFC has been in discussion with Municipal Emergency Managers on lessons learned from the 2013 flood, as well as what resources are needed in the short and long term for emergency management. |  | No